## Overview
Project Name: | Task Manager Application
Version: | v1.0
Test Type: | Manual Testing / Exploratory Testing
Test Environment: | Web Application (Localhost)
Description: | This document contains the defect log identified during testing of the Task Manager application (Version 1.0). The listed defects were discovered during test execution and documented for tracking and resolution purposes.
Notes: | Defects identified in version v1.0 are currently open and will be verified in the next build.
Test Summary: | All identified defects from v1.0 were fixed and verified successfully in v1.1.

## Version History
Version | Description | Date | Remarks
v1.0 | Initial testing and defect identification | 2025-02-20 | Bugs logged
v1.1 | Bug fixes applied and retesting completed | 2025-02-22 | All critical issues fixed

## Bug Report- Task Manager
Bug ID | Bug Title | Module | Environment | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Reference | Comments
TM-BUG-001 | The task title allows only special characters | Create Task | Web ¦ Chrome ¦ Localhost | User is logged in | 1. Open Create Task page 2. Enter only special characters in Title field 3. Click Save | The system should show validation error and prevent submission | The task is created successfully even when title contains only special characters | Medium | Medium | Open | Attached in Version 1.0 | Attached in Version 1.1
TM-BUG-002 | Bulk action buttons not visible after selecting multiple tasks | Task List | Web ¦ Chrome ¦ Localhost | User has multiple tasks | 1. Go to Task List 2. Select multiple tasks using checkboxes | Bulk action buttons (Delete/Complete) should appear | The tasks appear selected but no bulk action buttons are shown | Medium | Medium | Open | Attached in Version 1.0 | Attached in Version 1.1

## Version 1.0
TM-BUG-001
TM-BUG-002

## Version 1.1
TM-BUG-001_Fixed
TM-BUG-002_Fixed